## Introduction
Risk registers are often put on the back burner given they are strategic in nature and often conceptual documents for things that may happen. In the light of immediate issues, they are often neglected or not done.
However, in a situation like for example COVID-19, they become important tools to understand and develop plans in a crisis. And getting in the practice of building and maintaining risk registers now may mean you can (if you are not already) start creating registers for other areas of your work with schools, or operations in your office/work teams.
Risk registers correlate to the rubric here:
The fields in the tab ‘Risk Matrix’ can be completed for each risk, with the risk noted first on the left and then the mitigation action and residual risk on the right. Both have the same matrix/grid for determining the overall rating for each respectively. Explanations to guide completing each field in the comments triangles in the top left-hand corners are also provided.
The tab ‘risk ratings’ will help to understand how to plot this.
If you were making risk registers for school and or your OP office, many of these would run over a period of months or years, so complete with this in mind.
A good place to develop risk registers are during or as a result of strategy development meetings and plans, and it goes without saying - the more input from staff and team members the better they are likely to be. So getting input into their creation, but also checking in regularly with staff to update them would be useful.

## Risk Matrix
Please fill in the requested details below
Project title
Project start date
Project end date
Date Matrix Updated
[6 empty] | Inherent Risk |  |  |  |  | Residual Risk
RISK EXPLANATION | [8 empty] | RISK MITIGATION
Number | Risk date | Risk title | Risk category | Risk Owner | Description of risk | Probability | Impact | Overall | Action | Mitigating Action | Probability of Mitigating Action | Residual Impact | Overall | Status | Within appetite | What's changed
1
Note on G7: Inherent risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. For example, if you were to do nothing to combat the risk from materalising what level of risk rating would this pose?
Note on L7: The residual risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact.
Note on B9: Please enter in the date that you added the identified risk into this register using the format: DD/MM/YYYY The risk date does not change as risks are eveolve across quarters or as they are deemed to be closed. They remain as a historical record of when the risk was first identified.
Note on C9: Please give your identified risk a succinct single sentence title. Example entry: Upcoming election impacts on the ability to deliver the programme
Note on D9: There are six categories by which risks now need to be categorised. A contextual risk is one that is present in the space/location in which you are working. For example, risk that arise or are present in a conflict zone, a drought-affected region or a cultural setting. A delivery risk is a situation/event that will impact you or your partners' ability to deliver the programme. For example, the low resource capacity of your implementing partner results in the programme not delivering against its stated objectives. A safeguarding risk is an occurence that could pose a threat to the protection of the health, well-being and human rights of individuals, which allow people — especially children, young people and vulnerable adults — to live free from abuse, harm and neglect. An operational risk is one that could affect the day-to-day operation of the programme. An example may be a shortage of medications in-country or a logisitical disruption. A fiduciary risk is one that arises when funds are not used for the intended purposes; do not achieve value for money; and/or are not properly accounted for within the project. A reputational risk is one that will pose detriment to your organisation's reputation or public image due to certain activities, associations or perceptions. Please choose the relevant risk category from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on E9: Please specify the owner of the risk. Who is responsible for monitoring and taking action on this identified risk? The person could be within your organisation or within your downstream implementing partner organisation. There can only be one risk owner per risk. We request that you enter their full name, their job title and specify which organisation they are from, so that MannionDaniels/DFID know who to contact if necessary. Example entry: Mireille Massouka Bih, Project Manager, Education Partnerships Group
Note on F9: To describe risk please outline the cause, event and impact succinctly in 1-3 sentences. Example entry: An election is taking place in the next year, and there is a possibility a new party could create a law that would make our work more difficult.This would make carrying out our work significantly harder as we will have to carry out our project with a different approach to make sure we are operating within the law.
Note on G9: Please refer to the second tab 'Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. The probability risk ratings are listed along the left side of the matrix. Inherent risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Please choose the probability risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on H9: Please refer to the second tab 'Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. The impact risk ratings are listed along the bottom of the matrix. Inherent risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Please choose the impact risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on I9: In order to identify the overall risk rating, please refer to the second tab 'DFID Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. For example, if the pobability of your risk is 'Likely' and the impact is 'Major' the overall rating will be 'Severe' as the intersection of these two factors is the dark red box with the associated rating of 'Severe'. Inherent risk is the rating of the risk that exists as it stands or naturally occurs, prior to any mitigating actions being put in place. Please choose the overall risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on J9: Pick one of four actions to be taken against risks: tolerate, transfer, terminate, treat. Transferring Risk can be achieved through the use of various forms of insurance, or the payment to third parties who are prepared to take the risk on behalf of the organisation. Tolerating Risk is where no action can be easily taken to mitigate or reduce a risk and the presence of the risk is tolerated. Terminating Risk simply involves risk elimination. This can be done by altering or removing an inherently risky process or practice to eliminate the risk. Treating Risk is a method of controlling risk through actions that reduce the likelihood of the risk occurring or minimise its impact prior to its occurrence. There are also contingent measures that can be developed to reduce the impact of an event once it has occurred. Please choose the action from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on K9: Stephanie Schlipper: Please detail the actions that the risk owner(s) will take to mitigate against the risk and if there are any controls that can be put in place or exercised to manage the risk. Example entry: Various scenarios will be explored around changes to any laws that would impact directly or indirectly on the project. Research will be conducted into the opposition parties' positions on those key laws and alternative approaches will be explored and developed in case those laws are changed following the election. These actions will ensure we are prepared and can adapt quickly within a range of outcomes.
Note on L9: Please refer to the second tab 'Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. The probability risk ratings are listed along the left side of the matrix. The residual risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. Please choose the residual probability risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on M9: Please refer to the second tab 'Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. The impact risk ratings are listed along the bottom of the matrix. The residual risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. Please choose the impact risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on N9: In order to identify the overall risk rating, please refer to the second tab 'DFID Risk Rating' which presents the matrix for combining probability with impact to achieve the overall rating. For example, if the pobability of your risk is 'Likely' and the impact is 'Major' the overall rating will be 'Severe' as the intersection of these two factors is the dark red box with the associated rating of 'Severe'. The residual risk is the rating of the risk if all mitigation actions are successfully and effectively implemented. You can expect the residual risk to be lower than the inherent risk due to the actions taken the mitigate against the event occurence or impact. Please choose the overall risk rating from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on O9: A status will need to be ascribed to your identified risk. Please state whether it is open, emerging or closed. Open means that it is present and/or ongoing. Closed means that it the risk is no longer relevant or has been resolved. Emerging means that it has not been fully realised as a present risk but is on the horizon and gaining momentum. Please choose the risk status from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear. When a risk is deemed closed, please move the row in question to the bottom of the table and grey out the cells to indicate that the risk is resolved. It is requested that closed risks remain within the risk register to maintain a historical record across the project lifetime.
Note on P9: Risk appetite is defined as “the amount of risk to which the organisation is prepared to accept, tolerate or be exposed to at any point in time". Please state whether the identified risk is within your articulated risk appetite outline above. Please choose yes or no from the drop down menu in this column. Once you click on the cell the dropbox arrow will appear.
Note on Q9: This 'What's changed' column does not need to be filled in when you add in a new risk to the register. It can be left blank when it is a new risk identified for the quarter. It will need to be filled in when the next quarterly submission of the risk register is made, providing a brief summary of what has changed since the risk was entered originally. What led to it being resolved? What event occured that led to the risk increasing, decreasing or remianing steady in rating? How have you treated, transfered or terminated the risk? Example entry: The election has now taken place and the ruling party remained in power. Therefore, no laws have been changed and we are continuing our programme as normal.

## Risk Ratings
Overall Risk Ratings
Please identify the overall rating of an identified risk by finding the intersection of your probability and impact ratings in the matrix below and cross-referencing the colour of the cell with the four risk ratings below.
Minor
Moderate
Major
Severe
Likelihood vs. Impact Matrix
LIKELIHOOD | Almost certain (5)
Likely (4)
Possible (3)
Unlikely (2)
Rare (1)
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Severe (5)
IMPACT
Action
Action
Monitoring
Monitoring

## Dropdown lists
Insignificant | Rare | Tolerate | Context | Yes
Minor | Unlikely | Transfer | Delivery | No
Moderate | Possible | Terminate | Safeguarding
Major | Likely | Treat | Operational
Severe | Almost certain |  | Fiduciary
Reputational
Steady | Open | High
Upwards | Closed | Medium
Downwards | Emerging | Low